Part I Essex Integrated Care Board Meeting, 16 July 2026

#### NHS Essex Communications and Engagement Strategy

#### Appendix 1: Internal Communications Delivery Plan

Summary Report

### Purpose

This delivery plan sets out how NHS Essex will use internal communications and engagement to support organisational effectiveness, culture, leadership visibility and staff involvement.

It supports delivery of:

- NHS Essex Communications, Engagement and Involvement Strategy

- Organisational Development (OD) Plan

- NHS Essex operating model

- Workforce priorities

- Corporate objectives

- Population Health Improvement Plan

### Strategic Context

2026/27 will be a significant year for NHS Essex as we:

- Establish a new organisational identity following the creation of NHS Essex

- Embed new governance arrangements

- Launch the Organisational Development Strategy

- Develop new ways of working

- Build a single organisational culture

- Support staff through organisational change

- Strengthen leadership visibility and engagement

- Deliver organisational priorities and improve outcomes for residents

Internal communications will play a key role in helping staff understand organisational priorities, connect to the organisation's purpose, influence decision-making and contribute to building a positive organisational culture.

Internal communications are everyone's business. While the Communications and Engagement Team provides strategic leadership and professional support, effective communication is the responsibility of all leaders and managers across NHS Essex.

Strategic principles

Internal communications will be:

Staff-centred - focused on what staff need to know, feel and do.

Leadership-led - visible, authentic leadership communications.

Two-way - creating opportunities for dialogue, listening and involvement.

Insight-led - shaped by staff feedback, engagement data and organisational insight.

Inclusive - accessible, equitable and reflective of our diverse workforce.

Prioritised - focused on organisational priorities and meaningful communication.

Strategic priorities

Priority 1: Building a shared NHS Essex culture

Supporting the development of a shared identity, values, behaviours and organisational culture.

Priority 2: Leadership communication and visibility

Ensuring leaders communicate consistently, visibly and authentically with staff.

Priority 3: Staff voice and involvement

Creating opportunities for staff to influence decisions, shape organisational development and contribute ideas.

Priority 4: Modern and effective communication channels

Providing accessible, engaging and effective channels that support communication, collaboration and engagement.

Strategic Outcomes

- Outcome 1: Staff understand NHS Essex's vision, priorities and objectives.

Measures:

Staff pulse survey results

Staff briefing feedback

Staff survey results

Understanding of organisational priorities

- Outcome 2: Staff feel informed about decisions that affect them and their work.

- Measures:

Communication effectiveness scores

Staff feedback

Staff survey results

Pulse survey results

- Outcome 3: Leaders communicate consistently, visibly and effectively.

Measures:

Leadership visibility measures

Staff confidence in leadership

Staff briefing attendance

Leadership communication activity

- Outcome 4: Staff feel able to influence, shape and contribute to the development of NHS Essex.

- Measures:

Participation rates

Staff network engagement

Staff Partnership Forum activity

Staff feedback themes

"You said, we listened" actions

- Outcome 5: A positive organisational culture is established and embedded.

Measures:

Staff survey results

Values and behaviours programme milestones

Staff retention indicators

Organisational culture feedback

Strategic content framework

Content will align to: Making Health Services Better in Essex

Supporting themes:

- Organisational vision

- PHIP priorities

- OD strategy

- New operating model

- Governance changes

- Workforce wellbeing

- Leadership communications

- Staff recognition

- Equality, diversity and inclusion

- Learning and development

### Key audiences

Primary audiences:

- NHS Essex staff

- Senior leaders

- Line managers

Secondary audiences:

- Board members

- Staff network leaders

- Communications champions

### Key channels

| Channel | Purpose |
| --- | --- |
| Intranet | Primary information hub |
| Viva Engage | Discussion, collaboration and dialogue |
| Staff briefings | Leadership visibility and organisational updates |
| Team briefings | Local engagement and communication |
| Staff bulletin | Organisational news and updates |
| Leadership blogs | Context, narrative and leadership visibility |
| Staff events | Engagement and involvement |
| Pulse surveys | Listening and organisational insight |
| Staff networks | Inclusion, engagement and staff voice |

### Success Measures

Staff understanding

80% of staff attending staff briefings report they understand the organisational priorities.

80% of staff attending staff briefings report they understand key organisational changes.

Leadership visibility

At least 75% of staff report they have seen or heard from a senior leader in the previous three months.

Monthly leadership communication activity delivered as planned.

Staff engagement

Staff briefing attendance maintained or increased year on year.

Pulse survey participation exceeds 60%.

Participation in engagement activities increases year on year.

Communication effectiveness

Staff bulletin open rates maintained above 60%.

Intranet engagement increases year on year.

Staff rate internal communications as effective through survey feedback.

Staff voice

Quarterly "You said, we listened" updates published.

Staff networks active and represented across the organisation.

Staff feedback themes reviewed quarterly.

Culture and organisational development

Values and behaviours framework developed and launched by September 2026.

Values embedded through organisational development activity by March 2027.

Staff survey indicators relating to communication, involvement and culture improve over time.

### Governance

The delivery plan will be monitored through:

Quarterly reporting to Executive Team

Communications and Engagement Team performance reporting

Organisational Development governance arrangements

Staff survey and pulse survey reporting

### Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Staff information overload | Prioritised communications and channel governance. |
| Lack of leadership engagement | Leadership communication expectations and support. |
| Low staff participation | Increased opportunities for engagement and feedback. |
| Inconsistent communication across teams | Manager communication support and guidance. |
| Change fatigue | Clear communication, listening and staff involvement. |

### Appendix A – Internal communications implementation plan 2026/27

Priority 1: Building a shared NHS Essex culture

| Objective | Activity | Timeline | Lead | Success measure |
| --- | --- | --- | --- | --- |
| Develop NHS Essex values and behaviours | Review legacy ICB values and behaviours to identify common themes | July-August 2026 | OD / Comms | Review completed |
| Develop NHS Essex values and behaviours | Staff engagement programme including workshops, drop-ins, online survey and staff briefing discussions | July-September 2026 | OD / Comms | Minimum 40% staff participation |
| Develop NHS Essex values and behaviours | Develop final values and behaviours framework | September 2026 | OD | Framework approved |
| Launch organisational values | Organisation-wide launch campaign | October 2026 | Comms | 80% awareness among staff |
| Embed values into organisational culture | Integrate values into induction, appraisal, recruitment and recognition processes | October 2026-March 2027 | OD / HR | Implementation milestones achieved |
| Build organisational identity | Develop "Making Health Services Better in Essex" internal narrative and messaging framework | Q3 2026 | Comms | Narrative adopted across communications |
| Celebrate staff contribution | Introduce regular staff recognition stories and case studies | Monthly | Comms | Minimum one story per month |

Priority 2: Leadership communication and visibility

| Objective | Activity | Timeline | Lead | Success measure |
| --- | --- | --- | --- | --- |
| Increase leadership visibility | Monthly staff briefings with CEO and Executive Team | Monthly | Comms/ Executive Team | Attendance maintained or increased |
| Increase leadership visibility | Executive blogs and leadership updates | Monthly | Executive Team | One leadership communication per month |
| Improve communication cascade | Develop manager briefing framework | September 2026 | Comms | Framework implemented |
| Support leaders to communicate effectively | Comms toolkit for managers and senior leaders | October 2026 | Comms / OD | Toolkit launched |
| Increase access to leaders | Leadership Q&A sessions | Quarterly | Executive Team | Minimum 75% positive feedback |
| Strengthen executive visibility | Video updates from executive directors | Bi-monthly | Comms | Engagement monitored |
| Build leadership trust | Publish "You asked, we listened" responses following staff feedback | Quarterly | Comms | Four updates published |

Priority 3: Staff voice and involvement

| Objective | Activity | Timeline | Lead | Success measure |
| --- | --- | --- | --- | --- |
| Strengthen staff voice | Launch quarterly pulse surveys | Quarterly | Comms / OD | Response rate above 60% |
| Support Staff Partnership Forum | Establish communication channels and reporting arrangements | July 2026 | Comms | Forum updates published |
| Support staff networks | Promote network activity and opportunities for involvement | Monthly | Comms | Increased network participation |
| Improve feedback loops | Publish "You said, we listened" updates | Quarterly | Comms | Four updates published |
| Increase staff involvement | Staff consultation and engagement activity on major organisational changes | Ongoing | Comms / OD | Participation targets achieved |
| Gather organisational insight | Analyse staff feedback themes and report findings | Quarterly | Comms / OD | Quarterly insight reports produced |

Priority 4: Modern and effective communication channels

| Objective | Activity | Timeline | Lead | Success measure |
| --- | --- | --- | --- | --- |
| Develop intranet as primary staff hub | Deliver Phase 2 intranet improvements | 2026/27 | Comms | Improvement programme completed |
| Improve intranet content governance | Introduce content standards and ownership model | September 2026 | Comms | Governance framework agreed |
| Strengthen staff bulletin | Review content structure and effectiveness | August 2026 | Comms | Open rate maintained above 60% |
| Deliver regular organisational updates | Publish staff bulletin | Fortnightly | Comms | Delivery maintained |
| Improve channel performance | Develop communication dashboard and reporting framework | October 2026 | Comms | Dashboard implemented |
| Improve accessibility | Ensure all internal communication channels meet accessibility standards | Ongoing | Comms | Compliance maintained |
| Strengthen digital engagement | Increase use of Viva Engage and interactive content | Ongoing | Comms | Engagement increases year-on-year |